## Risk Register
NexusAI Risk Register - Q4 2025
Last Updated: January 2, 2026 ¦ Owner: Sarah Chen, VP Finance
ID | Risk Category | Risk Description | Likelihood | Impact | Risk Score | Mitigation Strategy | Owner
R001 | Financial | Cash runway exhaustion before Series B close | Medium | Critical | High | Bridge financing option, cost reduction contingency | Marcus Chen
R002 | Financial | Series B delayed beyond Q1 2026 | Low | Critical | Medium | Multiple investor conversations in parallel | Maya Rodriguez
R003 | Market | Enterprise sales cycle elongation | High | Medium | High | Pipeline diversification, mid-market focus | Rachel Foster
R004 | Market | Competitive response from Kinaxis/SAP | Medium | Medium | Medium | Speed-to-value differentiation, customer success | Lisa Martinez
R005 | Product | Supplier risk module delivery delay | Medium | High | High | Dedicated team, scope lock, weekly tracking | David Park
R006 | Product | Mobile app quality issues at GA | Medium | Medium | Medium | Extended beta, staged rollout | Lisa Martinez
R007 | Operational | Key person dependency (ML team) | High | High | Critical | Accelerate ML hiring, documentation | David Park
R008 | Operational | Cloud cost overrun | Medium | Low | Low | Reserved instances, cost optimization sprint | Carlos Mendez
R009 | Compliance | SOC 2 audit findings | Low | Medium | Low | Remediation in progress, buffer time built in | Carlos Mendez
R010 | Compliance | GDPR non-compliance for EU expansion | Low | High | Medium | EU data center deployment, legal review | Carlos Mendez
R011 | People | Hypergrowth culture dilution | Medium | Medium | Medium | Values-based hiring, culture initiatives | Maya Rodriguez
R012 | Customer | Customer concentration (top 3 = 42%) | Medium | High | High | New logo diversification focus | Rachel Foster
R013 | Customer | Mid-market churn acceleration | Medium | Medium | Medium | Health scoring, proactive CS intervention | Rachel Foster
R014 | Reputational | Negative word-of-mouth / competitor FUD | Medium | Medium | Medium | Customer reference program, PR response | Jennifer Walsh
RISK SUMMARY
Critical Risks: 1
High Risks: 4
Medium Risks: 7
Low Risks: 2
TOP RISKS FOR BOARD ATTENTION
1. R007 - Key person dependency in ML team (bus factor risk)
2. R001 - Cash runway if Series B delays
3. R005 - Supplier risk module delivery (competitive impact)