## Backlog Analysis
Product Engineering - Project Backlog & Resource Analysis
Analysis Date: January 5, 2026
Current Team Capacity: 8 engineers
Available Engineering Hours (Q1): 3,328 hours (8 people x 52 days x 8 hrs)
Project | Priority | Estimated Hours | Required Skills | Target Quarter | Status | Business Impact
API v3 Migration | P0 - Critical | 1200 | Backend, DevOps | Q1 2026 | In Progress (40%) | Customer commitment - $2M ARR at risk
Mobile App Redesign | P0 - Critical | 800 | Mobile, Frontend | Q1 2026 | Blocked - No capacity | Market competitiveness
Security Compliance (SOC2) | P0 - Critical | 600 | Security, DevOps | Q1 2026 | In Progress (20%) | Required for enterprise deals
Performance Optimization | P1 - High | 400 | Backend, Database | Q1 2026 | Not Started | Customer complaints increasing
Analytics Dashboard v2 | P1 - High | 500 | Frontend, Data | Q2 2026 | Not Started | Product differentiation
CI/CD Pipeline Overhaul | P1 - High | 300 | DevOps | Q1 2026 | Blocked - No capacity | Engineering velocity
Customer Portal Refresh | P2 - Medium | 450 | Frontend, Backend | Q2 2026 | Not Started | Customer satisfaction
Automated Testing Suite | P2 - Medium | 350 | QA, Backend | Q2 2026 | Not Started | Quality improvement
Documentation Overhaul | P2 - Medium | 200 | Technical Writing | Q2 2026 | Not Started | Support ticket reduction
Microservices Refactor | P3 - Low | 800 | Backend, DevOps | Q3 2026 | Planning | Technical debt reduction
CAPACITY ANALYSIS
Total Backlog (P0-P2): | 4,800 hours
Q1 Committed Work: | 3,000 hours
Q1 Available Capacity: | 3,328 hours
Q1 Capacity Gap: | -672 hours (20% shortfall)
KEY INSIGHT: Even at 100% utilization, team cannot deliver Q1 commitments.
Adding 3 engineers would provide 1,248 additional hours, closing the gap.