# Project Phoenix - Stakeholder Update

Date: October 15, 2025
Prepared by: James Chen, Project Manager
Distribution: Executive Team, TechCorp Leadership
Classification: Confidential

# Executive Summary

Project Phoenix continues to make strong progress toward our November 28th delivery commitment. Key achievements this period include successful completion of SSO integration and significant performance improvements. The team remains focused on quality delivery and client satisfaction.

# Status Overview

## On Track (Green)

Core Platform Stability - All major features complete and functioning

Multi-Tenant Architecture - Deployed and validated

Workflow Automation Engine - Complete and in client testing

SSO Integration - Successfully integrated with TechCorp Azure AD

Data Retention Policies - Development complete, in QA

Client Relationship - Strong engagement, weekly sync calls productive

## Monitoring (Yellow)

Performance Optimization - Additional tuning required for large datasets

QA Cycle - Bug volume slightly higher than projected; team is addressing

## Requires Attention (Red)

No critical blockers at this time.

# Key Accomplishments This Period

SSO Integration Complete: SAML 2.0 integration with Azure AD successfully deployed. TechCorp IT has validated the configuration and approved for production use.

Performance Improvements: Implemented caching layer and query optimizations. Dashboard load times improved by 60% for large datasets.

Security Audit Passed: Third-party penetration test completed with no critical findings. Minor recommendations implemented.

Workflow Automation in UAT: Client operations team actively testing automation features. Early feedback is positive.

# Timeline to Delivery

Target Delivery Date: November 28, 2025

Remaining Milestones:

October 22: Feature freeze - All development complete

November 5: QA sign-off - Testing cycle complete

November 12: UAT sign-off - Client acceptance

November 20: Pre-production deployment

November 28: Production go-live

# Risk Management

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| UAT feedback delays | Low | Medium | Daily sync calls scheduled |
| Bug discovery in QA | Medium | Low | Buffer in schedule; team prepared |
| Performance edge cases | Low | Medium | Monitoring in place; rapid response |

# Budget Status

Revised Budget: $1,176,000
Spend to Date: $1,020,000 (87%)
Projected Final: $1,176,000 (On Budget)

Note: Revised budget reflects approved scope changes throughout the project. All change orders were documented and approved by TechCorp prior to work commencing.

# Client Feedback

"The workflow automation feature is exactly what we needed. Our operations team is already identifying processes to automate." - Thomas Park, VP Engineering, TechCorp

"The demo yesterday was impressive. The multi-tenant isolation gives us confidence for subsidiary deployment." - Robert Martinez, CEO, TechCorp

# Next Steps

Complete remaining QA test cases (Week of October 21)

Address any P1/P2 bugs from testing (Ongoing)

Conduct UAT training session with TechCorp users (October 28)

Begin UAT execution (November 1)

Finalize production deployment runbook (November 15)

# Summary

Project Phoenix is on track for successful delivery on November 28th. The team has overcome significant challenges and delivered a robust, feature-rich platform that meets TechCorp's evolving needs. We appreciate the continued partnership and support from all stakeholders.

Questions? Contact James Chen (james.chen@ourcompany.com)