## Budget Summary
PROJECT PHOENIX - BUDGET TRACKING
Final Report - December 2025
Category | Original Budget | Approved Changes | Revised Budget | Actual Spend | Variance | Variance %
Labor - Development | 480000 | 168000 | 648000 | 672000 | 24000 | 3.7%
Labor - Project Management | 72000 | 18000 | 90000 | 96000 | 6000 | 6.7%
Labor - QA | 60000 | 24000 | 84000 | 90000 | 6000 | 7.1%
Labor - Design | 48000 | 12000 | 60000 | 60000 | 0 | 0%
Infrastructure - Cloud Hosting | 36000 | 12000 | 48000 | 54000 | 6000 | 12.5%
Infrastructure - Dev/Test Environments | 18000 | 6000 | 24000 | 27000 | 3000 | 12.5%
Third-Party Services - Salesforce API | 12000 | 0 | 12000 | 12000 | 0 | 0%
Third-Party Services - HubSpot API | 9000 | 0 | 9000 | 9000 | 0 | 0%
Third-Party Services - Elasticsearch | 15000 | 6000 | 21000 | 24000 | 3000 | 14.3%
Security - Penetration Testing | 24000 | 0 | 24000 | 24000 | 0 | 0%
Security - Audit Services | 18000 | 12000 | 30000 | 36000 | 6000 | 20%
Training & Documentation | 12000 | 0 | 12000 | 12000 | 0 | 0%
Contingency Reserve | 36000 | -36000 | 0 | 0 | 0 | N/A
TOTAL | 840000 | 222000 | 1062000 | 1116000 | 54000 | 5.1%
BUDGET SUMMARY
Original Contract Value: | 840000
Approved Change Orders: | 336000
Revised Contract Value: | 1176000
Actual Total Cost: | 1176000
VARIANCE FROM ORIGINAL
Dollar Amount: | 336000
Percentage Over Budget: | 40%
CHANGE ORDER BREAKDOWN
Change Order | Description | Amount | Approved Date
CO-001 | Multi-tenant Support | 120000 | 2025-05-28
CO-002 | Custom Field Support | 48000 | 2025-06-25
CO-003 | Workflow Automation Engine | 96000 | 2025-07-20
CO-004 | SSO/SAML Integration | 36000 | 2025-09-12
CO-005 | Data Retention Policies | 24000 | 2025-10-10
CO-006 | Additional Security Audit | 12000 | 2025-11-08
Total Change Orders: | 336000
NOTES
- All change orders were approved by client prior to work commencing
- Project came in on revised budget (within 5.1% variance)
- Original contingency absorbed into scope change work
- Client acknowledged value delivered exceeds cost increase