## Project Plan v1
Phase | Deliverable | Start Date | End Date | Duration (weeks) | Owner | Status | Dependencies
Phase 1: Foundation | Development Environment Setup | 2025-03-15 | 2025-03-28 | 2 | David Park | Planned | None
Phase 1: Foundation | Database Schema Design | 2025-03-15 | 2025-03-28 | 2 | Sarah Kim | Planned | None
Phase 1: Foundation | Authentication Module | 2025-03-22 | 2025-04-11 | 3 | Maria Santos | Planned | Environment Setup
Phase 2: Core Features | Dashboard Module | 2025-04-05 | 2025-05-02 | 4 | Alex Turner | Planned | Authentication
Phase 2: Core Features | Reporting Engine | 2025-04-19 | 2025-05-23 | 5 | Sarah Kim | Planned | Dashboard
Phase 2: Core Features | Data Integration Layer | 2025-05-03 | 2025-06-06 | 5 | David Park | Planned | Database Schema
Phase 3: Advanced | Notification System | 2025-05-24 | 2025-06-20 | 4 | Michael Brown | Planned | Core Features
Phase 3: Advanced | Search & Filtering | 2025-06-07 | 2025-07-04 | 4 | Alex Turner | Planned | Data Integration
Phase 3: Advanced | Data Import/Export | 2025-06-21 | 2025-07-18 | 4 | Michael Brown | Planned | Reporting Engine
Phase 4: Polish | Performance Optimization | 2025-07-05 | 2025-07-25 | 3 | David Park | Planned | All Features
Phase 4: Polish | Security Hardening | 2025-07-19 | 2025-08-08 | 3 | Maria Santos | Planned | All Features
Phase 4: Polish | UI/UX Polish | 2025-07-26 | 2025-08-15 | 3 | Jennifer Liu | Planned | All Features
Phase 5: Launch | QA & Testing | 2025-08-09 | 2025-08-29 | 3 | QA Team | Planned | Polish Complete
Phase 5: Launch | UAT Support | 2025-08-23 | 2025-09-05 | 2 | All | Planned | QA Complete
Phase 5: Launch | Production Deployment | 2025-09-01 | 2025-09-01 | 0.5 | DevOps | Planned | UAT Approved
PROJECT SUMMARY
Project Start: | 2025-03-15
Project End: | 2025-09-01
Total Duration: | 24 weeks
Team Size: | 6 engineers
ASSUMPTIONS
- No major scope changes after requirements sign-off
- Client provides timely feedback (< 3 days)
- All third-party integrations have documented APIs
- Team remains stable throughout project