## Project Plan v2
Phase | Deliverable | Original End | Revised End | Slip (weeks) | Owner | Status | Notes
Phase 1: Foundation | Development Environment Setup | 2025-03-28 | 2025-03-28 | 0 | David Park | Complete | On track
Phase 1: Foundation | Database Schema Design | 2025-03-28 | 2025-03-28 | 0 | Sarah Kim | Complete | On track
Phase 1: Foundation | Authentication Module | 2025-04-11 | 2025-04-15 | 0.5 | Maria Santos | Complete | Minor delays on OAuth
Phase 2: Core Features | Dashboard Module | 2025-05-02 | 2025-05-02 | 0 | Alex Turner | Complete | On track
Phase 2: Core Features | Reporting Engine | 2025-05-23 | 2025-05-23 | 0 | Sarah Kim | Complete | On track
Phase 2: Core Features | Data Integration Layer | 2025-06-06 | 2025-06-20 | 2 | David Park | In Progress | Salesforce API issues
NEW | Multi-Tenant Support | - | 2025-07-15 | NEW | David Park | In Progress | Scope change #1
Phase 2: Core Features | User Permissions System | 2025-06-20 | 2025-06-25 | 0.5 | Maria Santos | In Progress | Dependent on multi-tenant
Phase 3: Advanced | Notification System | 2025-06-20 | 2025-07-15 | 3.5 | Michael Brown | Planned | Delayed by multi-tenant
Phase 3: Advanced | Search & Filtering | 2025-07-04 | 2025-08-08 | 5 | Alex Turner | Planned | Delayed by dependencies
Phase 3: Advanced | Data Import/Export | 2025-07-18 | 2025-09-22 | 9 | Michael Brown | Planned | Pushed significantly
Phase 4: Polish | Performance Optimization | 2025-07-25 | 2025-10-10 | 11 | David Park | Planned | Pushed to end
Phase 4: Polish | Security Hardening | 2025-08-08 | 2025-10-24 | 11 | Maria Santos | Planned | Pushed to end
Phase 4: Polish | UI/UX Polish | 2025-08-15 | 2025-10-31 | 11 | Jennifer Liu | Planned | Pushed to end
Phase 5: Launch | QA & Testing | 2025-08-29 | 2025-11-07 | 10 | QA Team | Planned
Phase 5: Launch | UAT Support | 2025-09-05 | 2025-11-21 | 11 | All | Planned
Phase 5: Launch | Production Deployment | 2025-09-01 | 2025-11-28 | 12.5 | DevOps | Planned | NEW TARGET DATE
REVISION SUMMARY
Previous Target: | 2025-09-01
New Target: | 2025-11-28
Schedule Impact: | +12.5 weeks
SCOPE CHANGES ABSORBED
1. Multi-tenant support (client request)
2. Custom field support (client request)
3. Workflow automation (client request)
RISKS
- Additional scope changes could push date further
- Multi-tenant refactor has cascading impact
- Integration dependencies not fully resolved
Revision Date: 2025-06-15
Revised by: James Chen