## Project Plan v3 - Final
Phase | Deliverable | Original Plan | Final Actual | Total Slip | Owner | Status | Key Learnings
Phase 1 | Development Environment Setup | 2025-03-28 | 2025-03-28 | 0 weeks | David Park | Complete | On track
Phase 1 | Database Schema Design | 2025-03-28 | 2025-03-28 | 0 weeks | Sarah Kim | Complete | On track
Phase 1 | Authentication Module | 2025-04-11 | 2025-04-15 | +0.5 weeks | Maria Santos | Complete | OAuth complexity underestimated
Phase 2 | Dashboard Module | 2025-05-02 | 2025-05-02 | 0 weeks | Alex Turner | Complete | On track
Phase 2 | Reporting Engine | 2025-05-23 | 2025-05-20 | -0.5 weeks | Sarah Kim | Complete | Team exceeded expectations
Phase 2 | Data Integration Layer | 2025-06-06 | 2025-06-25 | +2.5 weeks | David Park | Complete | Third-party API issues
Phase 2 | User Permissions System | 2025-06-20 | 2025-06-22 | +0.5 weeks | Maria Santos | Complete | Multi-tenant dependency
SCOPE+ | Multi-Tenant Support | N/A | 2025-07-15 | NEW +6 weeks | David Park | Complete | Major architecture change
SCOPE+ | Custom Field Support | N/A | 2025-08-05 | NEW +4 weeks | Sarah Kim | Complete | Flexibility request
SCOPE+ | Workflow Automation | N/A | 2025-09-10 | NEW +8 weeks | David Park | Complete | Client priority
SCOPE+ | SSO Support (SAML) | N/A | 2025-10-15 | NEW +3 weeks | Maria Santos | Complete | Compliance requirement
SCOPE+ | Data Retention Policies | N/A | 2025-10-28 | NEW +2 weeks | Sarah Kim | Complete | Compliance requirement
SCOPE+ | API Rate Limiting | N/A | 2025-09-12 | NEW +1 week | Maria Santos | Complete | Security enhancement
Phase 3 | Notification System | 2025-06-20 | 2025-07-15 | +3.5 weeks | Michael Brown | Complete | Delayed by dependencies
Phase 3 | Search & Filtering | 2025-07-04 | 2025-08-12 | +5.5 weeks | Alex Turner | Complete | Elasticsearch learning curve
Phase 3 | Mobile Responsiveness | N/A | 2025-09-08 | NEW +2 weeks | Jennifer Liu | Complete | Quality improvement
Phase 3 | Data Import/Export | 2025-07-18 | 2025-09-28 | +10 weeks | Michael Brown | Complete | Deprioritized for scope changes
Phase 4 | Performance Optimization | 2025-07-25 | 2025-10-22 | +12 weeks | David Park | Complete | Critical path stretched
Phase 4 | Security Hardening | 2025-08-08 | 2025-11-15 | +14 weeks | Maria Santos | Complete | Two security issues found
Phase 4 | UI/UX Polish | 2025-08-15 | 2025-11-08 | +12 weeks | Jennifer Liu | Complete | Delayed but high quality
Phase 5 | QA & Testing | 2025-08-29 | 2025-11-12 | +10.5 weeks | QA Team | Complete | More bugs than expected
Phase 5 | UAT Support | 2025-09-05 | 2025-12-05 | +13 weeks | All | Complete | Client very engaged
Phase 5 | Production Deployment | 2025-09-01 | 2025-12-10 | +14 weeks | DevOps | Complete | SUCCESSFUL LAUNCH
FINAL PROJECT SUMMARY
Original Target: | 2025-09-01
Actual Delivery: | 2025-12-10
Total Schedule Slip: | 14 weeks (3 months)
Slip Percentage: | 58% over original estimate
SCOPE CHANGE IMPACT
Total Scope Changes: | 23
Major Scope Changes: | 6 (shown above)
Scope Change Effort: | ~24 weeks additional work
OUTCOME
Client Satisfaction: | HIGH - Exceeded expectations
Product Quality: | HIGH - Stable, performant
Launch Success: | Zero critical issues at go-live
Final Version Date: 2025-12-15
Prepared by: James Chen