# Project Phoenix - Scope Change Log

Document Control: Final Version
Project ID: PHX-2025
Last Updated: December 15, 2025
Prepared by: James Chen, Project Manager

# Executive Summary

Total Scope Changes: 23
Major Changes (>$20K impact): 6
Medium Changes ($5K-$20K impact): 8
Minor Changes (<$5K impact): 9

Total Schedule Impact: +14 weeks
Total Budget Impact: +$336,000 (40% of original budget)

# Major Scope Changes

## SC-001: Multi-Tenant Architecture Support

Requested By: TechCorp (Robert Martinez, CEO)
Request Date: 2025-05-28
Approved Date: 2025-05-30
Completion Date: 2025-07-15

Description: Add multi-tenant support to allow TechCorp to deploy the platform across their five subsidiaries with complete data isolation and shared administration capabilities.

Business Justification: TechCorp requires white-label deployment capability for subsidiary companies. This feature enables significant contract expansion opportunity.

Impact Assessment:
- Schedule: +6 weeks (database refactor, query updates, security review)
- Budget: +$120,000
- Risk: HIGH - Architectural change affects all components
- Resources: Required full team involvement

Lessons Learned: Multi-tenancy should be a Day 1 decision. Retrofitting is expensive. Future projects should explicitly confirm single vs. multi-tenant requirements in discovery.

## SC-002: Custom Field Support

Requested By: TechCorp (Thomas Park, VP Engineering)
Request Date: 2025-06-25
Approved Date: 2025-06-28
Completion Date: 2025-08-05

Description: Allow administrators to create custom fields on all major entities (users, reports, workflows) with support for text, number, date, dropdown, and multi-select field types.

Business Justification: Each TechCorp subsidiary has unique data requirements. Custom fields enable flexibility without code changes.

Impact Assessment:
- Schedule: +4 weeks
- Budget: +$48,000
- Risk: MEDIUM - Schema changes, validation complexity

Lessons Learned: Custom field requirements often emerge during implementation. Consider including basic custom field support in base platform.

## SC-003: Workflow Automation Engine

Requested By: TechCorp (Operations Team)
Request Date: 2025-07-20
Approved Date: 2025-07-22
Completion Date: 2025-09-10

Description: Build a no-code workflow automation system allowing users to create trigger-action rules (e.g., "when report status changes to Approved, notify finance team and update dashboard").

Business Justification: TechCorp operations team currently manages processes manually. Automation will save estimated 15+ hours/week.

Impact Assessment:
- Schedule: +8 weeks (complex feature)
- Budget: +$96,000
- Risk: HIGH - New subsystem with complex dependencies

Lessons Learned: Workflow automation is a common enterprise requirement. Should be evaluated as potential base feature for similar projects.

## SC-004: SSO Support (SAML 2.0)

Requested By: TechCorp (IT Security Team)
Request Date: 2025-09-12
Approved Date: 2025-09-15
Completion Date: 2025-10-15

Description: Integrate SAML 2.0 SSO to allow TechCorp employees to authenticate using their corporate identity provider (Azure AD).

Business Justification: Corporate security policy requires all enterprise applications to support SSO. Blocker for production deployment.

Impact Assessment:
- Schedule: +3 weeks
- Budget: +$36,000
- Risk: MEDIUM - Well-understood integration pattern

Lessons Learned: SSO is standard enterprise requirement. Should be included in original scope for any enterprise project.

## SC-005: Data Retention Policies

Requested By: TechCorp (Legal/Compliance)
Request Date: 2025-10-10
Approved Date: 2025-10-12
Completion Date: 2025-10-28

Description: Implement configurable data retention policies including automatic archival and deletion of data based on age, with audit logging of all retention actions.

Business Justification: GDPR and SOX compliance requirements mandate data retention controls. Compliance blocker for go-live.

Impact Assessment:
- Schedule: +2 weeks
- Budget: +$24,000
- Risk: LOW - Bounded scope, clear requirements

Lessons Learned: Compliance requirements should be discovered early. Add compliance checklist to requirements gathering.

## SC-006: Enhanced Security Audit

Requested By: Internal (Maria Santos, Security Lead)
Request Date: 2025-11-08
Approved Date: 2025-11-08
Completion Date: 2025-11-15

Description: Engage third-party security firm for comprehensive penetration testing following discovery of file upload vulnerability.

Business Justification: Security vulnerability in file upload handling discovered during internal audit. Additional testing required to ensure no other vulnerabilities exist before production deployment.

Impact Assessment:
- Schedule: +1 week
- Budget: +$12,000
- Risk: LOW - Defensive measure

Lessons Learned: Security audits should be scheduled earlier in project lifecycle to allow time for remediation.

# Medium Scope Changes (Summary)

| ID | Change | Date | Schedule | Budget |
| --- | --- | --- | --- | --- |
| SC-007 | API Rate Limiting | 2025-08-20 | +1 week | +$12,000 |
| SC-008 | Audit Trail Export | 2025-11-10 | +0.5 weeks | +$8,000 |
| SC-009 | Mobile UI Optimization | 2025-08-10 | +2 weeks | +$18,000 |
| SC-010 | Bulk Operations API | 2025-07-15 | +1 week | +$10,000 |
| SC-011 | Dashboard Customization | 2025-06-15 | +1.5 weeks | +$15,000 |
| SC-012 | Enhanced Reporting Filters | 2025-08-05 | +1 week | +$12,000 |
| SC-013 | Email Template Customization | 2025-09-01 | +0.5 weeks | +$6,000 |
| SC-014 | Advanced Search Operators | 2025-08-15 | +1 week | +$10,000 |

# Minor Scope Changes (Summary)

| ID | Change Description | Budget |
| --- | --- | --- |
| SC-015 | Password complexity requirements | +$3,000 |
| SC-016 | Session timeout configuration | +$2,500 |
| SC-017 | Export filename customization | +$1,500 |
| SC-018 | Notification preference granularity | +$4,000 |
| SC-019 | Dashboard widget reordering | +$3,500 |
| SC-020 | Timezone display preferences | +$2,000 |
| SC-021 | Search result pagination options | +$2,500 |
| SC-022 | Report scheduling frequency options | +$3,000 |
| SC-023 | User avatar support | +$1,500 |

# Recommendations for Future Projects

Establish formal scope change process with defined approval workflow

Require impact analysis (schedule + budget) before scope change approval

Include scope freeze milestone in project plan with client acknowledgment

Build contingency buffer explicitly for scope changes (20-30%)

Conduct architectural decision sessions early to avoid late pivots

Include enterprise requirements (SSO, multi-tenancy, compliance) in discovery checklist