# 2024 Survey Action Items - Status Tracker

Last Updated: December 2024

# Background

Following the 2024 Employee Engagement Survey, leadership committed to the following action items. This document tracks progress as of year-end 2024.

# Action Item Status

## 1. Launch IC Career Track Framework

Owner: HR - Talent Development

Target Date: Q2 2024

Status: PARTIAL

Notes: Framework designed and approved. Pilot launched in Engineering (July 2024). Full rollout delayed to Q1 2025 due to headcount freeze. Engineering pilot feedback positive.

## 2. Quarterly 'Ask Leadership Anything' Sessions

Owner: CEO Office

Target Date: Q1 2024 onwards

Status: COMPLETED

Notes: Four ALA sessions held in 2024 (Feb, May, Aug, Nov). Average attendance: 67%. Survey feedback on leadership communication improved slightly (+0.1). Sessions will continue in 2025.

## 3. Workload Review - Customer Support

Owner: VP Customer Support

Target Date: Q2 2024

Status: NOT STARTED

Notes: Deprioritized due to cost reduction initiatives. Team headcount actually reduced by 2 FTE in Q3. Ticket quotas increased. This item needs to be re-elevated for 2025.

## 4. Workload Review - Operations

Owner: VP Operations

Target Date: Q2 2024

Status: PARTIAL

Notes: Process automation project launched (May 2024). Some efficiency gains realized. However, restructuring in Q3 increased workload for remaining team members. Net impact unclear - needs assessment.

## 5. Compensation Benchmarking Study

Owner: HR - Total Rewards

Target Date: Q3 2024

Status: COMPLETED

Notes: Study completed September 2024. Key findings: base salaries competitive (P50), equity grants below market (P35), benefits above average. Recommendation to improve equity grants in 2025 merit cycle. Board approved 15% increase to equity pool.

## 6. Manager Training Program Expansion

Owner: HR - Learning & Development

Target Date: Q2 2024

Status: COMPLETED

Notes: Program expanded from 2 days to 5 days. Modules added: Difficult Conversations, Remote Team Management, Career Coaching. 34 managers completed training in 2024. Manager effectiveness scores improved in Q3/Q4.

# Summary

Completed: 3 of 6 items (50%)
Partial Progress: 2 of 6 items (33%)
Not Started: 1 of 6 items (17%)

Key Gap: Customer Support workload concerns were not addressed and may have worsened. This should be a priority focus area for 2025. The item was deprioritized during cost reduction efforts, but employee sentiment in this area is likely to have declined.